## Sheet1
Week | Project milestones | Difficulty
2021-01-09 | Create Project plan in Excel | Medium
| Create Git repository, add the code | Easy
| Create Trello board | Easy
2021-09-02 | Configure automated CI using GitHub Actions | Medium
| Configure on premise agent for Azure DevOps | Hard
2021-09-06 | Configure CD using Azure DevOps | Hard
| Test | Medium
2021-09-09 | Prepare Demo | Medium
| Submit project for Udacity's review | Easy
Goals
Complete fully automated CI / CD
Submit project for Udacity's review
Year | 1st quarter | 2nd quarter | 3rd quarter | 4th quarter
2021 | Gather data from the market, get data from all stakeholders | Build the ML backend using Flask | Build the FE using Vue.js | Deliver to production San Francisto's house predictions using fully automated CI / CD